## Data Tracking - Procurement
Vendor Name | Component | Expected Date | Actual Date | Delay (Days)
Vendor A | Motor | 2024-12-01 | 2024-12-02 | 1
Vendor B | Control Panel | 2024-12-03 | 2024-12-05 | 2
Vendor C | Gear Assembly | 2024-12-05 | 2024-12-06 | 1

## Data Tracking - Lead Time
Process Stage | Standard Time (Days) | Actual Time (Days) | Variance (%)
Design | 5 | 6 | 20
Procurement | 10 | 12 | 20
Assembly | 7 | 8 | 14.3
Testing | 3 | 4 | 33.3

## Dashboards
Metric | Type | Value
Lead Time Variance | Current | 20%
Lead Time Variance | Target | 10%
On-Time Orders | Current | 75%
On-Time Orders | Target | 90%
Inventory Turnover | Current | 1.5
Inventory Turnover | Target | 2

## Cost-Benefit Analysis
Category | Item | Amount ($)
Cost | Training | 10000
Cost | Tool Implementation | 20000
Savings | Inventory Reduction | 15000
Savings | Lead Time Improvement | 25000
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Implemention plan chart
Status | Count of Phase
Completed | 1
In Progress | 1
Pending | 3
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Implementation Plan
Phase | Action Item | Owner | Timeline | Status
Diagnostics | Map current process | Team A | Dec 2024 | Completed
Planning | Design solutions | Team B | Jan 2025 | In Progress
Pilot | Test scheduling tool | Team C | Feb 2025 | Pending
Implementation | Rollout tools and training | Team D | Mar 2025 | Pending
Monitoring | Track KPIs | Team E | Apr 2025 | Pending

## Metric value status
Metric | Current Value | Target Value | Variance (%) | Status
Lead Time Variance | 20% | 10% | 100 | Above Target | The Status can be "Above Target," "On Target," or "Below Target," depending on whether the Current Value is better, equal to, or worse than the Target Value.
On-Time Orders | 75% | 90% | -16.6667 | Below Target
Inventory Turnover | 1.5 | 2 | -25 | Below Target
Production Efficiency | 80% | 85% | -5.8824 | Below Target
Delivery Performance | 95% | 95% | 0 | On Target
Order Fulfillment | 90% | 100% | -10 | Below Target
Inventory Accuracy | 98% | 99% | -1.0101 | Below Target
Supplier Performance | 85% | 90% | -5.5556 | Below Target
Quality Control | 92% | 95% | -3.1579 | Below Target
Scrap Rate | 3% | 2% | 50 | Above Target
Customer Satisfaction | 85% | 90% | -5.5556 | Below Target
Machine Downtime | 4% | 3% | 33.3333 | Above Target
Manufacturing Cost | 120000 | 110000 | 9.0909 | Above Target
Energy Consumption | 80% | 85% | -5.8824 | Below Target
Process Efficiency | 78% | 82% | -4.878 | Below Target
Safety Compliance | 95% | 100% | -5 | Below Target
Production Output | 10000 | 12000 | -16.6667 | Below Target
Labor Productivity | 90% | 92% | -2.1739 | Below Target
Waste Reduction | 5% | 3% | 66.6667 | Above Target
Return Rate | 2% | 1% | 100 | Above Target
Order Accuracy | 98% | 100% | -2 | Below Target
Inventory Levels | 50000 | 55000 | -9.0909 | Below Target
Customer Returns | 3% | 2% | 50 | Above Target
Packing Accuracy | 99% | 100% | -1 | Below Target
Production Delay | 7% | 5% | 40 | Above Target
Scrap Materials | 2% | 1% | 100 | Above Target
Customer Feedback | 75% | 80% | -6.25 | Below Target
Overproduction | 5% | 3% | 66.6667 | Above Target
Customer Retention | 85% | 90% | -5.5556 | Below Target
Inventory Shrinkage | 1% | 0.5% | 100 | Above Target
Productivity Rate | 85% | 90% | -5.5556 | Below Target
Rejection Rate | 4% | 3% | 33.3333 | Above Target
Return on Investment | 8% | 10% | -20 | Below Target
Stockouts | 3% | 2% | 50 | Above Target
Order Accuracy Rate | 98% | 99% | -1.0101 | Below Target
Yield Rate | 90% | 95% | -5.2632 | Below Target
Stock Turnover Rate | 5 | 6 | -16.6667 | Below Target
Supplier Defects | 2% | 1% | 100 | Above Target
Workforce Productivity | 85% | 90% | -5.5556 | Below Target